## Test Report
Total Modules
Total User Stories | 11 | S.No | User Story | Total No of Test cases | Test cases Passed | Test cases Failed
Test cases covered -- User Stories | 9 | 1 | L01 | 5 | 5 | 0
Test Cases Pending -- User Stories | 2 | 2
Integration and Data miration User stories |  | 3
Total Number of Test cases | 97 | 4
Test cases Executed | 95 | 5
Total test cases Passed | 73 | 6
Pending for Execution | 2 | 7
Total Test cases Failed | 3 | 8
Total Defects Observed | 18 | 9
Remarks |  | 10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
25

## Functional Test Cases
S.No | Module/Sub Module | User Story ID | Use Story Description | Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Status | Comments/Remarks
| Home Page/Login Page |  | SFDC Login page/Home page: After user login to SFDC application user should find "Home" page as default landing page. Under Home page user should find "Feed" , "Dashboards" , "Item to Approve", "Pending Visits", "My Task" and "Calendar" details. | TC_01 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display default JSW "Home" page. | As Expected | Pass
|  |  |  | TC_02 | Verify Home Page | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should navigate to Home page and user should find following details under Home page. "Feed" , "Dashboard", "Items to Approve", "Pending visits", "My Tasks", "Calendar" , "Search". | As Expected | Pass
|  |  |  | TC_03 | Validate "Feed" under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find Feed details automatically , if user click on "Hide Feed" all the Feed should hide. Ex: Any changes took place under user's Territory in terms of Hierarchy or any objects like Accounts or Leads those changes/updates should appear under Feed. | As Expected | Pass
|  |  |  | TC_04 | Verify other options under "Feed" | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find following sections under Feed. "Post" -- User can share any information through text message. "File" -- User can attach required file and share "New Event" -- User can create new Event directly here Once after created all above should appear under Feed. | As Expected | Pass
|  |  |  | TC_05 | Validate "Dashboard" under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find defined Dashboards . |  | Pending | No Dash boards are appearing.
|  |  |  | TC_06 | Validate "Pending visits" under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find Pending visits if any along with "New Visit" button. During monthly visit plan if user not visited as per the visit plan those details should appear in pending visits section under Home page. | As Expected | Pass
|  |  |  | TC_07 | Create Visits manually under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button 5) Click on "New Task" under Pending Visits section. | User should create new Visit Record. Note: We can find detailed visit record test cases under "Visit Record" user story. | As Expected | Pass
|  |  |  | TC_08 | Validate My Tasks under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find all task details under My Task section, if task status is "Open" system gives reminder automatically and user also have privilege to create new Task in "My Task" section under Home page. | As Expected | Pass
|  |  |  | TC_09 | Validate Calendar under Home page. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | All the Events/ New Meeting Requests should appear under Calendar section and user also have privileges to create new Event and new meeting request in Calendar section under Home page. | As Expected | Pass
|  |  |  | TC_10 | Verify "Search" field . | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should find "Search" field on top left side and it is also known as global search function. | As Expected | Pass
|  |  |  | TC_11 | check for a record through "Search" component. | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button 5) Enter required record in "Search" field. | User should find all the relevant records as search results. | As Expected | Pass
1 | Lead Management | L01 | Lead Landing page: User can login to Salesforce Application and have privilege to check all the Existing Lead Records based on the Permissions provided. | TC_12 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User id 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
2 |  |  |  | TC_13 | Select "Leads" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list | User should find all existing Lead records if available and "New" button where user can create new Lead by clicking on "New" button. | As Expected | Pass
3 |  |  |  | TC_14 | Verify all the Leads based on the "list view" option selected. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "View" dropdown list from "Lead's Home" page 4) Select any one of following list view options. a) All Open Leads b) My Unread Leads c) Recently Viewed Leads d) Today's Leads 5) Click on "Go" button.. | User can find all existing Lead's records related to login user based on list view selection. | As Expected | Pass
4 |  |  |  | TC_15 | Click on any Record from existing Records. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Select List view option. 3) Click on any Record from existing Record list | System display Lead detail page along with "Edit", "Delete", "Convert", "Clone" buttons along with other related list details. | As Expected | Pass
5 |  |  |  | TC_16 | Verify all related list items under Lead detail page. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing list 4) Scroll down the application | User can find following Related list items. a) Activities b) Visit Reports c) Open Activities d) Activity History e) Notes and Attachments f) Marketing Information | As Expected | Pass
| Lead Management | L02 | New Lead Creation: User can login to Salesforce Application and have privilege to create new Lead based on the Permissions provided. | TC_17 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_18 | Select "Leads" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list | User can find all existing Leads records if any and "New" button under Leads page. User can create new Lead by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_19 | Create New Lead | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find New Lead page | As Expected | Pass
|  |  |  | TC_20 | Verify all the field sections under New lead page. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find following Field sections , these can be modified/Added/Deleted with the help of System Admin. "Lead Information" "Personal Information" "Address Information" | As Expected | Pass
|  |  |  | TC_21 | Verify all the fields under "Lead Information" Section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find following Fields, these can be modified/Added/Deleted with the help of System Admin. "First Name" "Last Name" "Company" "Lead Status" "Enlistment Status" "Lead Source" "Rating" "Type of Products" User can enter all required fields to track Lead information. | As Expected | Pass
|  |  |  | TC_22 | Validate "First Name" and "Last Name" under lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find "Last Name" as mandatory and First Name and Last Name should appear in other areas like "Month Plan" creation ….Etc. | As Expected | Pass | I need information if any validation on First name and Last Name fields
|  |  |  | TC_23 | Validate "Company" and "Type of Products" under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find "Company" as mandatory text field where can enter competitor company name and user can select Type of Product which lead is selling. | As Expected | Pass
|  |  |  | TC_24 | Verify hover over button beside "Enlistment Status" pick list field under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Keep the cursor on Hover over button (I) beside "Enlistment Status" pick list. | While hover the cursor on hover over button(I) system should display "Depends on "Lead Status" it indicates user that "Enlistment Status" is depends on "Lead Status" pick list selection | As Expected | Pass
|  |  |  | TC_25 | Verify "Lead Status" and "Enlistment Status" under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | "Lead Status" is mandatory pick list field and "Enlistment status" is dependent pick list for "Lead Status". Based on the "Lead Status" pick list selection "Enlistment status" pick list field will be enabled. | As Expected | Pass
|  |  |  | TC_26 | Validate "Lead Status" and "Enlistment Status" under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Select "Enlisted" pick list value from "Lead Status" pick list.. | "Lead Status" is mandatory pick list field and it consists of following pick list values. "Open", "Working", "Enlisted", "Qualified". If user select "Enlisted" from pick list "Enlistment status" pick list should enable and display dependent pick list values where user can select required field. | As Expected | Pass
|  |  |  | TC_27 | Verify "Lead Category" under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Click on "category" pick list | User should find "Lead Category "I pick list with following values and based on selected value user can categorized the lead. "A" , "B" , "C" | As Expected | Pass
|  |  |  | TC_28 | Verify hover over button beside "Sub Type" pick list field under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Keep the cursor on Hover over button (I) beside sub-type button | While hover the cursor on hover over button(I) system should display "Depends on "Type" it indicates user that "Sub-type" is depends on "Type" pick list selection | As Expected | Pass
|  |  |  | TC_29 | Validate Lead "Type" and "Sub-Type "under Lead information section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Click on "Lead Type" pick list | User should find Lead "Type" pick list and "Sub-type" dependent pick list fields. If user select Pick list fields of "Trade" and "Non Trade" from "Type" pick list , "Sub-type" pick list should enable and display the dependent pick list values. | As Expected | Pass
|  |  |  | TC_30 | Verify all the fields under "Personal Information" Section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find following Fields, these can be modified/Added/Deleted with the help of System Admin. "Phone Number" text field "Mobile" text field "Email" Text field "Birth Date" Date field "Anniversary" Date field user can enter all required fields to track Personal information of a Lead. | As Expected | Pass
|  |  |  | TC_31 | Verify all the fields under "Address Information" Section. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. | User should find following Fields, these can be modified/Added/Deleted with the help of System Admin. "Street" Large text field "City" text field "State / Province" Text field "Zip/Postal code" Text field "Country" Text field user can enter all required fields to track Address information of a Lead. | As Expected | Pass
|  |  |  | TC_32 | Validate "Save" , "Save & New" , "Cancel" buttons | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "New" button. 4) Enter all Mandatory and Required fields 5) Click on "Save" / "Save & New" / "Cancel" buttons | After entered all the fields, If User click on "Save" button Lead Record should save and navigate to Lead detail page. If User Click on "Save & New" button Lead record should save and navigates to New Lead page If user click on "Cancel" button , all the fields which are entered will be cancelled and navigate to Lead home page | As Expected | Pass
|  | L03 | Lead Edit page: User can login to Salesforce Application and have privilege to Edit a Lead based on the Permissions provided. | TC_33 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_34 | Select "Leads" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list | User can find all existing Leads records if any and "New" button under Leads page. User can create new Lead by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_35 | Verify all the Leads based on the "list view" option selected. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "View" dropdown list from "Lead's Home" page 4) Select any one of following list view options. a) All Open Leads b) My Unread Leads c) Recently Viewed Leads d) Today's Leads 5) Click on "Go" button.. | User can find all existing Lead's records based on list view selection. | As Expected | Pass
|  |  |  | TC_36 | Click on any Record from existing Records. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Record list | System display Lead detail page along with "Edit", "Delete", "Convert", "Clone" buttons along with other related list details. | As Expected | Pass
|  |  |  | TC_37 | Edit a Lead by changing any of field value. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Records list 4) Click on Edit button on Lead detail page 5) Click on "Save" button | User should get Lead Edit page and can modify any field values, after modifying field values if click on save button Lead gets saved with modified field values. | As Expected | Pass
|  | L04 | Cloning a Lead: User can login to Salesforce Application and have privilege to create new Lead by using "Clone" option | TC_38 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_39 | Select "Leads" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list | User can find all existing Leads records if any and "New" button under Leads page. User can create new Lead by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_40 | Verify all the Leads based on the "list view" option selected. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "View" dropdown list from "Lead's Home" page 4) Select any one of following list view options. a) All Open Leads b) My Unread Leads c) Recently Viewed Leads d) Today's Leads 5) Click on "Go" button.. | User can find all existing Lead's records based on list view selection. | As Expected | Pass
|  |  |  | TC_41 | Click on any Record from existing Records. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Record list | System display Lead detail page along with "Edit", "Delete", "Convert", "Clone" buttons along with other related list details. | As Expected | Pass
|  |  |  | TC_42 | Create a new Lead Record by using clone. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Records list 4) Click on Clone button on Lead detail page 5) Click on "Save" button | User should get Lead Edit page with existing lead field values and can Enter/modify any field values, after modifying field values if click on save button new Lead gets saved . | As Expected | Pass
|  | L05 | Verification of Lead under Month Plan Creation: All the Leads which are created by a User should be visible during creating Month plan in order to select during his/her visit. | TC_43 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_44 | Navigate to "Month Plan" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list Users who are having privileges can view and edit Month plan | User can find all existing "Month Plan" records if any and "New" button under Month Plan home page. User can create new "Month Plan" by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_45 | Verify leads while creating new Month plan | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Select Leads under "Filter by" pick list from Filter custom data and verify Leads on right pane | User should find Leads which are created under Lead tab in order to select while creating Month plan (PJP) | As Expected | Pass
|  | L06 | Deleting a Lead: User can login to Salesforce Application and have privilege to Delete a Lead based on the Permissions provided. | TC_46 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_47 | Select "Leads" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list | User can find all existing Leads records if any and "New" button under Leads page. User can create new Lead by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_48 | Verify all the Leads based on the "list view" option selected. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on "View" dropdown list from "Lead's Home" page 4) Select any one of following list view options. a) All Open Leads b) My Unread Leads c) Recently Viewed Leads d) Today's Leads 5) Click on "Go" button.. | User can find all existing Lead's records based on list view selection. | As Expected | Pass
|  |  |  | TC_49 | Click on any Record from existing Records. | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Record list | System display Lead detail page along with "Edit", "Delete", "Convert", "Clone" buttons along with other related list details. | As Expected | Pass
|  |  |  | TC_50 | Delete a Lead . | 1) Login to JSW Application 2) Select "Leads" Tab from available Tabs. 3) Click on any Record from existing Records list 4) Click on Edit button on Lead detail page 5) Click on "Delete" button | User should get "Are you sure" pop up message if user click on "OK" button Lead record should be deleted. | As Expected | Pass
| Account Management | ACC_01 | Account Landing page: User can login to Salesforce Application and have privilege to check all the Existing Account Records based on the Permissions provided. | TC_51 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User id (Login with SO credentials) 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_52 | Select "Accounts" Tab from available Tabs. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. If "Accounts" Tab is not available on Application landing page, click on "+" and there we can find "Accounts" Tab from list | User should find all related Account records under Account page. Account details should Appear/Update automatically in sfdc from legacy system based on schedule run at backend. | As Expected | Pass
|  |  |  | TC_53 | Verify "list view" options available for Accounts. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. 3) Click on "View" dropdown list from "Account's Home" page | User should find following list view options to filter the Accounts. a) All Accounts b) My Accounts c) Recently Viewed Accounts
|  |  |  | TC_54 | Verify all the Accounts based on the "list view" option selected. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. 3) Click on "View" dropdown list from "Account's Home" page 4) Select any one of following list view options. a) All Accounts b) My Accounts c) Recently Viewed Accounts 5) Click on "Go" button.. | User should find related Account's records based on list view selection. If user select "All Accounts" , system display all types of accounts related to user. | As Expected | Pass
|  |  |  | TC_55 | Verify types of Accounts which are available. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. 3) Click on "View" dropdown list from "Account's Home" page 4) Select "All Accounts" from list view options. 5) Click on "Go" button.. | User should find following Account types. "Trade", "Non Trade" , "Depot" and these Account types will be segregated based on Account type field.
|  |  |  | TC_56 | Select on any Record from existing Records. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. 3) Select List view option. 3) Click on any Record from existing Record list | System should display Account detail page along with "Edit", "Delete", "Get Contacts" buttons along with other related list details. | As Expected | Pass
|  |  |  | TC_57 | Verify "Search" field . | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. | User should find "Search" field on top left side and it is also known as global search function.
|  |  |  | TC_58 | Select a Account record through "Search" component. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Accounts" Tab from available Tabs. 3) Enter any Record name/id in Search field. | User should find the record which is searching.
|  |  |  | TC_59 | Verify all related list items under Account detail page. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Account" Tab from available Tabs. 3) Click on any Record from existing list 4) Scroll down the application | User can find following Related list items. a) Opportunities b) Contracts c) Order Requests d) Orders e) Delivery f) Invoices g) Business Partners h) Market Information i) Visits j) Visit Reports k) Order Requests (Sub Dealer) l) Order Requests (Sales Promotor) j) Monthly Targets | As Expected | Pass
|  | ACC_02 | Business Partner Landing page: User can login to Salesforce Application and have privilege to check all the Existing Business Partners Records based on the Permissions provided. | TC_60 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User id (Login with SO credentials) 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_61 | Select "Business Partners" Tab from available Tabs. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partners" Tab from available Tabs. If "Business Partners" Tab is not available on Application landing page, click on "+" and there we can find "Business Partners" Tab from list | User should find all related Business Partner records under Business Partner page. Business Partner details should Appear/Update automatically in sfdc from legacy system based on schedule run at backend. | As Expected | Pass
|  |  |  | TC_62 | Verify "list view" options available for Business Partners. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partners" Tab from available Tabs. 3) Click on "View" dropdown list from "Business Partner's" Home page | User should find following list view options to filter the Business Partners. a) All Business Partners b) My Business Partners c) Recently Viewed Business Partners
|  |  |  | TC_63 | Verify all the Business Partners based on the "list view" option selected. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partners" Tab from available Tabs. 3) Click on "View" dropdown list from "Business Partner's Home" page 4) Select any one of following list view options. a) All Business Partners b) My Business Partners c) Recently Viewed Business Partners 5) Click on "Go" button.. | User should find related Business Partner records based on list view selection. If user select "All Business Partners" , system display all types of Business Partners related to user. | As Expected | Pass
|  |  |  | TC_64 | Verify types of Business Partners which are available. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partners" Tab from available Tabs. 3) Click on "View" dropdown list from "Business Partner's Home" page 4) Select "All Business Partners" from list view options. 5) Click on "Go" button.. | User should find following Business Partner types. "Sub Dealers", "Sales Promotors" , "MMC", "Sales Employees" and these Business Partner types will be segregated based on Business Partner type field.
|  |  |  | TC_65 | Select on any Record from existing Records. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partner" Tab from available Tabs. 3) Select List view option. 3) Click on any Record from existing Record list | System should display Business Partner detail page along with "Edit", "Delete", "Get Contacts" buttons along with other related list details. | As Expected | Pass
|  |  |  | TC_66 | Verify all related list items under Business Partner detail page. | 1) Login to JSW Application (Login with SO credentials) 2) Select "Business Partner" Tab from available Tabs. 3) Click on any Record from existing list 4) Scroll down the application | User can find following Related list items. a) Open Activities b) Activity History c) Activities d) Visits e) Orders f) Accounts | As Expected | Pass
| PJP and DSR ( Journey plan Management) | PJP_01 | Create Month Plan (Personal Journey Plan): User can create His/her Monthly journey plan in order to cover all Accounts, Leads , conduct campaigns…etc., to maintain visit frequency properly and improve sales. User should have option to select all the events ( Leads, Accounts, Sub Dealers, etc.) in to calendar with the use of drag and drop function by using filters on the sections. | TC_67 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name (SO Credentials) 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application. | As Expected | Pass
|  |  |  | TC_68 | Select "Month Plan (PJP)" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list | User can find all existing Month Plan records if any and "New" button under Month Plan page. User can create new Month plan by clicking on "New" button. | As Expected | Pass
|  |  |  | TC_69 | Create new personal journey plan (PJP). | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Leads" Tab is not available on Application landing page, click on "+" and there we can find "Leads" Tab from list 3) Click on "New" button. 4) Select Record type "PJP" from pick list and click on Continue button. 5) Select "Month" from pick list 6) Select "Year" from pick list 7) Click on "Create PJP" button | User should find Create Personal Journey plan landing page. | As Expected | Pass
|  |  |  | TC_70 | Verify "Create Personal Journey Plan" landing page. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button | User should find Personal Journey Plan(PJP) calendar with default "Sales Rep Name" , "Status" as "New Request" along with following features. 1) Sales Rep Name 2) Status 3) Plan From , To dates 4) Planned Visits 5) Visited Count 6) Days Planned 7) Monthly Calendar 8) Filter by pick list 9) Apply Filter button 10) Month , Week, day buttons 11) Save , PJP Tab buttons | As Expected | Pass
|  |  |  | TC_71 | Validate following fields under "Create Personal Journey Plan" landing page. 1) Sales Rep Name 2) Status 3) Plan From , To dates | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button | User should find "Sales Rep Name" as auto display field where it display the Logged in user name automatically "Plan From" , "To" fields will display automatically the calendar dates which user selected. "Status" - Default Status display as "New Request" | As Expected | Pass
|  |  |  | TC_72 | Validate "Filter by" pick list for SO. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan. | As Expected | Pass
|  |  |  | TC_73 | Validate "Filter by" pick list for ASM. | 1) Login to JSW Application with ASM Credentials. 2) Select "Month Plan" Tab from available Tabs. 3) Click on "New"/ "Edit" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan.
|  |  |  | TC_74 | Validate "Filter by" pick list for SSM. | 1) Login to JSW Application with SSM Credentials. 2) Select "Month Plan" Tab from available Tabs. 3) Click on "New"/ "Edit" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan. | Need to change expected results
|  |  |  | TC_75 | Validate "Filter by" pick list for ZSM. | 1) Login to JSW Application with ZSM Credentials. 2) Select "Month Plan" Tab from available Tabs. 3) Click on "New"/ "Edit" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan. | Need to change expected results
|  |  |  | TC_76 | Validate "Filter by" pick list for TSO. | 1) Login to JSW Application with TSO Credentials. 2) Select "Month Plan" Tab from available Tabs. 3) Click on "New"/ "Edit" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan.
|  |  |  | TC_77 | Validate "Filter by" pick list for TSH. | 1) Login to JSW Application with TSH Credentials. 2) Select "Month Plan" Tab from available Tabs. 3) Click on "New"/ "Edit" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required events | User should find following pick list options to select as Filter custom data. "Leads" , "Accounts", "Business Partners", "Project sites","C&F","Warehouse","Influencer","Territory","Event","General Visit". Based on selected pick list user also find dependent picklist ( Sub list) to select required picklist value in Journey plan.
|  |  |  | TC_78 | Validate "Apply Filter" button. | 1) Login to JSW Application with SO Credentials 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required pick list values and dependent pick list values. 7) Click on "Apply Filter" button | User should find all the data / Pick list values which are created/Available . Ex : Select "Leads" under Filter by pick list --> select "Trade" under Type dependent pick list --> select "A" under Category dependent pick list and click on "Apply Filter" button based on this selections/ Filters , what ever the data available that should display . | As Expected | Pass
|  |  |  | TC_79 | Select required Data like Leads, Accounts, …etc. in to personal Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required pick list values and dependent pick list values from right pane. 7) Click on "Apply Filter" button 8) Drag and drop the required events from right pane to calendar. | User should drag required events from right pane based on the filter selection and drop them in to calendar. | As Expected | Pass
|  |  |  | TC_80 | Create and Save new Personal Journey plan (PJP). | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required pick list values and dependent pick list values from right pane. 7) Click on "Apply Filter" button 8) Drag and drop the required events from right pane to calendar. 9) Click on "Save" button | New Personal Journey plan should save , user should find "Edit", "Clone", "Submit Month", "Summary" buttons on top and all events should display on calendar. If user hover over on events , hover message should display. New Personal Journey plan status should display with "New Request" After Drag and Drop the events, a visit record to corresponding day plan should generate. | As Expected | Pass
|  |  |  | TC_81 | Verify "Approval History" and "Week Plan" Related list. | 1) Login to JSW Application 2) Create and save Personal Journey plan. | New Personal Journey plan should save and "Approval History" and "Week Plan" related list should display at bottom of journey plan. User should find all the Approval history data under Approval History section. If user click on "Week plan" related list user can observe all the weeks with start date and End date details | As Expected | Pass
|  |  |  | TC_82 | Validate following fields on Personal Journey Plan page. "Sales Rep Name" "Status" "Plan From" "Plan To" | 1) Login to JSW Application 2) Create and Save Personal Journey plan | User who created journey plan should find his/her name beside "Sales Rep Name" field. User should find the status of Personal journey as mentioned below. After Personal Journey saved, status should display as "New Request". After personal journey plan send it for approval to Approving Authority , status should display as "Submitted for Approval" If Approving Authority Approved the Personal Journey plan , status should display as "Approved" If Approving Authority Rejected the Personal Journey plan , status should display as "Rejected". User should find Calendar start date and end date of planned month. | As Expected | Pass
|  |  |  | TC_83 | Verify hover message of Events on Personal journey plan calendar. | 1) Login to JSW Application 2) Create and Save Personal Journey plan 3) Hover over on any even on Calendar | User should find Title, Start date , region of that particular events | As Expected | Pass
|  |  |  | TC_84 | Validate "Planned Visits" section on Personal Journey Plan page. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record | User should find "Planned Visits" section and count of Planned visits get updated based on the events which are selected and dragged and dropped on calendar. If user edit the journey plan and add new event , the planned visit count should increase and if event is deleted the count should decreased. | As Expected | Pass
|  |  |  | TC_85 | Validate "Visited Count" section on Personal Journey Plan page. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record | User should find "Visited Count" section and count of Visited count get updated based on the events which are user visited. If a event is visited by user it display as green color background on Personal Journey plan page. | As Expected | Pass
|  |  |  | TC_86 | Validate "Days Planned" section on Personal Journey Plan page. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record | User should find "Number of Days Planned" section and count of Number of Days planned get updated based on the events which are selected ( Drag and Dropped) by users on number of days. If event is selected on holidays, even that day also counts in Days planned. | As Expected | Pass
|  |  |  | TC_87 | Validate differences of visit types on Personal Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record | User should find different colors based on the visits to Events. For Pending events it should display with Yellow For Events which are visited should display in green. For General visits it should display with blue For events which are not visited after planning should display in pink. | As Expected | Pass
|  |  |  | TC_88 | Compare map pointer between Day Planned visit address and Actual visited address | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record 4) Click on day plan block on Calendar. | User should navigate to Day Plan record which would consist of Planned map and the actual map
|  | PJP_02 | Edit Personal Journey Plan: User can Edit Personal Journey plan and after Approved/Rejected user can switch to Week (or) Day plans from Calendar to modify as per the requirements and user can delete any Event ( Lead , Account, Sub Dealer….etc.) and can add new Event . User can edit Personal journey plan when it is in status as "New Request" , "Rejected" , "Approved" and not possible to edit when it is in "Send it for Approval status" | TC_89 | Edit Personal Journey plan. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Select required Month plan which is New Request/Approved/Rejected from available list. 4) Click on "Edit" button. | User navigates to Personal Journey plan edit page and can edit Personal journey plan if it is as "New Request" status (or) "Rejected" status (or) "Approved" status. User also find "Save" and "PJP" buttons. | As Expected | Pass
|  |  |  | TC_90 | Edit events ( Leads , Accounts …etc. ) on journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Select required Month plan from available list. 4) Click on "Edit" button. 5) Add/Delete Events from Calendar based on Filter custom data. | User can Add or Delete events as per required changes. User can delete Events by clicking (single click) on events. User can add events by drag the required events from right pane based on the filter selection and drop them in to calendar | As Expected | Pass
|  |  |  | TC_91 | Observe (Switch to) Week and Day plans on Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing Month plan from available list. | User can find "Week" and "Day" buttons and once click on "Week"/ "Day" button system navigates to Current week / current day plan on calendar. | As Expected | Pass
|  |  |  | TC_92 | Edit Month plans (Personal Journey plan) on Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Click on existing Month plan from available list. 4) Click on Edit button 5) Click on Week/Day 6) Add/Delete Events from Calendar based on Filter custom data. 6) Click on Save button. | User can edit month (week/Day) plan by Add or Delete events as per required changes. User can delete Events by clicking (single click) on events. User can add events by drag the required events from right pane based on the filter selection and drop them in to calendar | As Expected | Pass
|  |  |  | TC_93 | Navigate to selected event's record from calendar and observe "General visit" component. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on existing "Personal Journey Plan "record 4) Click on Events under calendar 5) Click on "General visit" component (Event) under calendar | System should navigate to Event (Lead, Account (or) Sub Dealer record. If user click on "General Visit" component , system navigates to Visit record. | As Expected | Pass
|  |  | Clone Personal Journey Plan: User can create new Journey plan by using Clone functionality . user can select existing Approved Journey plan to clone and user can modify as per the requirements , delete any Event ( Lead , Account, ….etc.) and add new Event . Once user clone the Journey plan one template gets create after making changes on them if user click on Save pjp , journey plan gets saved. User can Clone Personal journey plan when it is in status as "New Request" , "Approved" , "Rejected" and not possible to Clone when it is in "Send it for Approval status" | TC_94 | Clone Personal Journey plan. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Select Month plan which is New Request/Approved/Rejected from available list. 4) Click on "Clone" button. | User navigates to Personal Journey plan edit page and can edit Personal journey plan if it is as "New Request" status (or) "Rejected" status (or) "Approved" status. User also find "Save" and "PJP" buttons. | As Expected | Pass
|  |  |  | TC_95 | Edit "Plan for Month" and "Plan for Year" fields. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Select Month plan which is New Request/Approved/Rejected from available list. 4) Click on "Clone" button. | User should edit "Plan for the Month" and "Plan For Year" fields by selecting required pick list value.
|  |  |  | TC_96 | Create Journey plan by cloning other journey plan. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. If "Month Plan" Tab is not available on Application landing page, click on "+" and there we can find "Month Plan" Tab from list 3) Select Month plan which is New Request/Approved/Rejected from available list. 4) Click on "Clone" button. 5) Edit "Month" , "Year" fields 5) Click on "Create PJP" button. | New Personal journey plan should create and navigate to new personal journey plan landing page.
|  |  |  | TC_97 | Verify new Template Record for the cloned month under "Month Plan" object. | 1) Clone Personal journey plan 2) Navigate to Month plan Object | user should find New Template record for the cloned month.
|  |  |  | TC_98 | Validate new Template Record for the cloned month under "Month Plan" object. | 1) Clone Personal journey plan 2) Navigate to Month plan Object 3) Click on New Template Record | User should find Journey plan calendar which is cloning , user can edit "Plan for the Month" and "Plan For Year" fields. User should also find "PJP Tab" , "Create PJP" buttons.
|  |  |  | TC_99 | Create Journey plan from Template. | 1) Clone Personal journey plan 2) Navigate to Month plan Object 3) Click on New Template Record 4) Edit "Month" , "Year" fields 5) Click on "Create PJP" button. | New Personal journey plan should create and navigate to new personal journey plan landing page. User should find new dates under "Plan From" , "Plan To" fields
|  |  |  | TC_100 | Edit events ( Leads , Accounts, Sub Dealers) on journey plan calendar. | 1) Login to JSW Application 2) Create Personal Journey plan by cloning other journey plan. 3) Click on "Edit" | User can Add or Delete events as per required changes. User can delete Events by clicking (single click) on events. User can add events by drag the required events from right pane based on the filter selection and drop them in to calendar | As Expected | Pass
|  |  |  | TC_101 | Submit Month plan for Approval. | 1) Login to JSW Application 2) Create Personal Journey plan by cloning other journey plan. 3) Click on "Submit for Approval" button. | User should get pop up message stating that "Once you submit this record for approval , you might not be able to edit or recall…." along with "OK" and "Cancel" buttons. If user click on "OK" button, Month plan should send for approval to Approval hierarchy and email alert will be triggered automatically to Approval hierarchy, status of Personal Journey plan change to "Submitted for Approval" and user lose edit privileges of personal journey plan until Approval Hierarchy Approve/Reject the Personal Journey Plan. If user click on "Cancel" button , system navigates to Personal journey plan landing page.
|  | PJP_03 | Personal Journey Plan Approval Process: After creating Personal Journey plan user should send it for approval to his/her hierarchy. User have privilege to send for approval. After personal journey plan send for Approval to Approval authority, Status will be changed to "Request for Approval" and user should lose Edit privileges of Personal Journey plan. User's hierarchy (Manager) can review the Personal Journey plan and can Edit/Reject/Approve. After User's hierarchy Approved or Rejected , user again gets edit privileges on Personal Journey plan and user can edit journey plan on weekly (or) monthly basis and send it for approval to hierarchy. | TC_102 | Create and Save new Personal Journey plan (PJP). | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required pick list values and dependent pick list values from right pane. 7) Click on "Apply Filter" button 8) Drag and drop the required events from right pane to calendar for all week . 9) Click on "Save" button | New Personal Journey plan should save and all events should display on calendar. If we hover over on events , hover message should display. New Personal Journey plan status should display with "New Request" User can find "Submit Month" button. | As Expected | Pass
|  |  |  | TC_103 | Validate "Submit Month" button. | 1) Login to JSW Application 2) Create and Save Personal Journey plan | User should find "Submit Month" button which is enabled. | As Expected | Pass
|  |  |  | TC_104 | Submit Month plan for Approval. | 1) Login to JSW Application 2) Create and Save Personal Journey plan 3) Select the week which need to send for approval 4) Click on "Submit for Approval" button. | User should get pop up message stating that "Once you submit this record for approval , you might not be able to edit or recall…." along with "OK" and "Cancel" buttons. If user click on "OK" button, Month plan should send for approval to Approval hierarchy and email alert will be triggered automatically to Approval hierarchy, status of Personal Journey plan change to "Submitted for Approval" and user lose edit privileges of personal journey plan until Approval Hierarchy Approve/Reject the Personal Journey Plan. If user click on "Cancel" button , system navigates to Personal journey plan landing page. | As Expected | Pass
|  |  |  | TC_105 | Validate "Submit Week" button. | 1) Login to JSW Application with valid credentials 2) Create and Save Personal Journey plan 3) Send Personal journey plan for Approval | User should find "Submit Week" button which is enabled. This option available for the users after Personal journey plan (Month plan) Approved/Rejected by Approving authority once. | As Expected | Pass
|  |  |  | TC_106 | Click on "Submit Week" button. | 1) Login to JSW Application with valid credentials 2) Create and Save Personal Journey plan 3) Send Personal journey plan for Approval process | User should find all the weeks with check box along with start date , End date and Status. User should also find "Submit for Approval" , "PJP" Tabs on top. | As Expected | Pass
|  |  |  | TC_107 | Submit Week plan for Approval. | 1) Login to JSW Application with valid credentials 2) Create and Save Personal Journey plan 3) Send Personal journey plan for Approval process 4) Observed Personal journey plan is Approved (or) Rejected. 5) click on Approved/Rejected Journey plan 6) Click on Submit Week button 7) Select the week which need to send for approval 8) Click on "Submit for Approval" button. | User should get pop up message stating that "Once you submit this record for approval , you might not be able to edit or recall…." along with "OK" and "Cancel" buttons. If user click on "OK" button Week plan should send for approval to Approval hierarchy. If user click on "Cancel" button , system navigates to Personal journey plan landing page.
|  |  |  | TC_108 | Observe Month plan landing page view of Approval Hierarchy (Manager) | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab | Hierarchy User can find all his/her user's Month plan records which are sent for approval process.
|  |  |  | TC_109 | Navigate to Personal Journey plan landing page. | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab 3) Click on month plan Record which is Required to Approve (or) Reject | User navigates to Personal Journey plan landing page.
|  |  |  | TC_110 | Verify all the fields under Personal Journey plan landing page. | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab 3) Click on month plan Record which need to Approve (or) Reject | User should find following fields under Personal Journey plan landing page. "Join" , "Summary" , "PJP Tab" buttons on top and "Reassign" , "Approve" and "Reject" options available beside personal journey plan which is sent for approval under Approval History section.
|  |  |  | TC_111 | Approve Personal journey plan . | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Select User specific PJP which need to Approve 3) Click on Approve/Reject button. 4) Enter Comments under Comments text box. 5) Click on "Approve" button. | Personal journey plan should get approved and re navigates to personal journey plan landing page , under Approval history section overall status display as "Approved". All the history of Approvals will be tracked under Approval history section. According to Hierarchy Personal journey plan record should display to users. | As Expected | Pending | Need to check Hierarchy
|  |  |  | TC_112 | Reject Personal journey plan . | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Select User specific PJP which need to Approve 3) Click on Approve/Reject button. 4) Enter Comments under Comments text box. 5) Click on "Reject" button. | Personal journey plan should get Rejected and re navigates to personal journey plan landing page , under Approval history section overall status display as "Rejected" All the history of Approvals will be tracked under Approval history section. | As Expected | Pass
|  |  |  | TC_113 | Approve/Reject Personal journey plan through email alert . | 1) Login to respective email account with Approval hierarchy (Manager) credentials. 2) Click on the link which is available on email alert 3) Click on Approve/Reject button. 4) Enter Comments under Comments text box. 5) Click on "Approve"/"Reject" button. | Personal journey plan should get approved/Rejected and reanimates to personal journey plan landing page , under Approval history section overall status display as "Approved"/"Rejected" All the history of Approvals will be tracked under Approval history section. | As Expected | Pass
|  |  |  | TC_114 | Validate "PJP tab" functionality. | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab 3) Select User specific PJP from list 4) Click on PJP Tab. | User (Hierarchy) should navigate to personal journey plan landing page which is selected.
|  |  |  | TC_115 | "Join" on Personal Journey Plan calendar. | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab 3) Select User specific PJP from list | User (Hierarchy) should navigate to personal journey plan landing page of selected user , there User should find "Join" button.
|  |  |  | TC_116 | Validate "Join" functionality. | 1) Login to JSW Application with valid Approval hierarchy (Manager) credentials. 2) Click on "Month Plan" Tab 3) Select User specific PJP from list 4) Click on Join. 5) Select the events on calendar 6) Click on Join again. | User (Hierarchy) should select required events which he/she wants to join for visit . If user (Hierarchy manager) selected events to join for the first time in the month , automatically personal journey plan gets created for that month and all the selected events should add to that journey plan. If personal journey plan calendar already created , all the selected events which are selected should added to journey plan calendar.
|  |  |  | TC_117 | Verify all the records for Sales Officer | 1) Enter the URL on selected browser 2) Enter valid User name (Sales Officer Credentials) 3) Enter Password 4) Click on Login button | Logged in user (Sales Officer) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (Sales Officer). 2) All the Events which are created by user(Sales Officer) and TSO which is assigned to SO. 3) All the Leads which is created by user(SO) and Accounts which are related to user
|  |  |  | TC_118 | Verify all the records for Area Sales Manager | 1) Enter the URL on selected browser 2) Enter valid User name (Area Sales Manager) 3) Enter Password 4) Click on Login button | Logged in user (ASM) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (ASM)., SO , Technical service head and branding manager 2) All the Leads, Accounts which are created by user(Sales Officer) who is reporting.
|  |  |  | TC_119 | Verify all the records for State Sales head. | 1) Enter the URL on selected browser 2) Enter valid User name (State Sales Head) 3) Enter Password 4) Click on Login button | Logged in user (SSM) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (SSM)., ASM , Technical service head and branding manager 2) All the Leads, Accounts which are created by users who is reporting.
|  |  |  | TC_120 | Verify all the records for Zonal Sales head. | 1) Enter the URL on selected browser 2) Enter valid User name (Zonal Sales Head) 3) Enter Password 4) Click on Login button | Logged in user (ZSM) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (SSM)., ASM , Technical service head and branding manager 2) All the Leads, Accounts which are created by users who are reporting.
|  |  |  | TC_121 | Verify all the records for Technical Service Officer. | 1) Enter the URL on selected browser 2) Enter valid User name (Technical Service Officer) 3) Enter Password 4) Click on Login button | Logged in user (TSO) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (TSO), SO, Branding manager. 2) All the Leads, Accounts which are created by user (TSO) and SO who is assigned.
|  |  |  | TC_122 | Verify all the records for Technical Service head. | 1) Enter the URL on selected browser 2) Enter valid User name (Zonal Sales Head) 3) Enter Password 4) Click on Login button | Logged in user (ZSH) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (TSH)., ASM , Technical service Officer and branding manager 2) All the Leads, Accounts which are created by users who are reporting.
|  |  |  | TC_123 | Verify all the records for Branding Manager. | 1) Enter the URL on selected browser 2) Enter valid User name (Zonal Sales Head) 3) Enter Password 4) Click on Login button | Logged in user (Branding Manager) should find all the records as mentioned below. 1) All the personal journey plans which are created by user (Branding Manager) , SO. 2) All the Leads, Accounts which are created by users who are reporting.
|  |  | Visit Records: While creating Personal Journey plan users should drag and drop the events ( Leads, Accounts .. . ...etc.) in to calendar. For every drag and drop of event should save a record in Visits Object associated to a Day Plan Object. User can Check in from visit record and add all the information during visit under Visit Report which is related list and check out. during check in and check out process, time will be captured in respective fields. If both the address details matches ( Event address which is added and check in address during visit) automatically "Visited" check box should checked and relevant event should turn in to green color background under journey plan calendar. | TC_124 | Create Personal Journey plan. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button . | User should find Create Personal Journey plan landing page.
|  |  |  | TC_125 | Select required events like Leads, Accounts, …etc. in to personal Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Click on "new" button 4) Select Month and Year from pick list 5) Click on "Create PJP" button 6) Click on "Filter by" pick list and select required pick list values and dependent pick list values from right pane. 7) Click on "Apply Filter" button 8) Drag and drop the required events from right pane to calendar 9) Click on Save button. | User should drag required events from right pane based on the filter selection and drop them in to calendar.
|  |  |  | TC_126 | Observe the visit record for the event (Lead,Account,Sub Dealer…etc.) under "Visit" Object. | 1) Login to JSW Application 2) Select "Visits" Tab from available Tabs. | User should navigate to Visits landing page and find Visit record with Unique Visit name (ID) along with Event details like Event type, Event name and created date.
|  |  |  | TC_127 | Verify Visit Record . | 1) Login to JSW Application 2) Select "Visits" Tab from available Tabs. 3) Click on Visit Record | User should navigate to visit record landing page and can find following features (buttons). "Edit" , "Check in" , "Delete" , "Clone" , "Sharing" User should also find following related list items. "Visit Reports" , "Open Activities" , "Activity History"
|  |  |  | TC_128 | Navigate to Visit Record from Personal Journey plan calendar. | 1) Login to JSW Application 2) Select "Month Plan" Tab from available Tabs. 3) Select Existing Month plan Record 4) Click on any event from Month plan Calendar | User should navigate to visit record landing page and can find following features (buttons). "Edit" , "Check in" , "Delete" , "Clone" , "Sharing" User should also find following related list items. "Visit Reports" , "Open Activities" , "Activity History"
|  |  |  | TC_129 | Validate all the fields under Visit record. | 1) Login to JSW Application 2) Navigate to Visit Record | User should find all the following fields under Visit Record. Visit Name , Account, Lead, Address, Type, Planned, Planned Date, Start, End, Visited, Check in Time, Check out Time.
|  |  |  | TC_130 | Observe the Visit name field under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | User should observe that Visit name should display default value which is non editable field.
|  |  |  | TC_131 | Check "Lead" , "Account" Fields under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | User should observe that if selected event on the calendar is Lead / Account, that should display and user can navigate to corresponding "Lead" or "Account" page by clicking on them.
|  |  |  | TC_132 | Verify Address field under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | Address is text field and this will be filled automatically based on the event which is selected on calendar .
|  |  |  | TC_133 | Verify "Type" field under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | Type field should display the type of the event automatically . Ex: Lead (or) Account (or) Sub Dealer….etc.
|  |  |  | TC_134 | Verify "Planned" field under visit record landing page. | 1) Login to JSW Application 2) Select "Visits" Tab from available Tabs. 3) Click on Visit Record | User should find a check box. If selected event is planned as per journey plan, check box should be checked automatically.
|  |  |  | TC_135 | Verify "Planned Date" field under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | Planned date field should display the date automatically based on the event selected on the journey plan calendar.
|  |  |  | TC_136 | Verify "Start" , "End" Date under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record | Start Date and End Date fields should display the date and time automatically based on the event selected on the journey plan calendar. Based on the number of events selected for the day on the calendar time should display, for every event default time difference should be one hour and automatically time starts with 9am.
|  |  |  | TC_137 | Validate Check in button. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. | User should observe Check in time automatically displayed on "Check in " field and visited location address.
|  |  |  | TC_138 | Verify new visit report. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Click on "New Visit Report" button under Visit Reports related list. | User should navigate to Visit Report Edit page with following field sections. "Information", "Collection Information", "Branding Related", "Supply chain Related"
|  |  |  | TC_139 | Validate all the fields under Information field section. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Click on "New Visit Report" button under Visit Reports related list. | User should find following fields under Information field section. "Visit Report Name" as mandatory text field. "Visit Type" as pick list field with "Planned". "Unplanned" pick list values. "Visit" as lookup field with default lookup value.
|  |  |  | TC_140 | Validate all the fields under Collection Information field section. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Click on "New Visit Report" button under Visit Reports related list. | User should find following fields under Collection Information field section. "Pending payment amount committed" as text field and user can enter payment details during visit. "Due Date Committed" is date field where user can select date from calendar
|  |  |  | TC_141 | Create and save Visit report. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Click on "New Visit Report" button under Visit Reports related list. 5) Enter all the fields and click on "Save" button. | Visit Report should save and display under Visit Record as Related list.
|  |  |  | TC_142 | Validate Check out button. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check out" button. | User should observe Check out time automatically displayed on "Check out" field and visited location address.
|  |  |  | TC_143 | Validate "Visited" field under visit record landing page. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Create Visit Report 5) Click on "Check out" button.. | Based on the mapping of visited location address and Event ( Lead, Account, Sub Dealer….etc.) address and both get mapped, "Visited" check box field get check automatically.
|  |  |  | TC_144 | Validate Event ( Lead , Account, …etc.) on Calendar which visited by a user. | 1) Login to JSW Application 2) Navigate to Visit Record 3) Click on "Check in" button. 4) Create Visit Report 5) Click on "Check out" button.. 6) Navigate to journey plan calendar and click on the Event which is visited. | User should find Event which is visited should display in green.
|  |  | General Visit/Un Planned Visit/Area Visits: During journey plan user may get chance to visit new / unlisted Leads. To cover those leads user have privilege to create as general visit, there user can create new lead and assign to visit report/visit record During journey plan user may get chance to visit unplanned Leads/Accounts. To cover those unplanned leads/Accounts user need to create visit report from Visit reports object and need to select Lead/Account which is not planned, once Visit report is saved Lead/Account should appear on Journey plan. | TC_145 | Check "General Visit" visit record. | 1) Login to JSW Application 2) Navigate to journey plan calendar 3) Click on "General Visit" Event on calendar | User should navigate to "General Visit" visit record.
|  |  |  | TC_146 | Verify "Lead" , "Account" fields under Visit record. | 1) Login to JSW Application 2) Navigate to journey plan calendar 3) Click on "General Visit" Event on calendar | User should observe "Lead" , "Account" both fields should display with empty.
|  |  |  | TC_147 | Navigate to "Visit Report" from General Visit record. | 1) Login to JSW Application 2) Navigate to journey plan calendar 3) Click on "General Visit" Event on calendar 4) Scroll down the page 5) Click on "New Visit Report" button under Visit Report related list. | User should navigate to Visit Report Record type page.
|  |  |  | TC_148 | Create new Lead from Visit Report. | 1) Login to JSW Application 2) Navigate to journey plan calendar 3) Click on "General Visit" Event on calendar 4) Scroll down the page 5) Click on "New Visit Report" button under Visit Report related list. 6) Select "Lead" from pick list 7) Click on Continue button 8) Click on "Lead" lookup field Magnifying glass icon 9) Click on New | User should find New Lead page with mandatory fields. |  |  | This feature not developed
|  |  |  | TC_149 | Create and save new Lead from Visit Report. | 1) Create New Lead from Visit Report 2) Click on Save Button | New Lead gets saved and display under Lead record list in Visit Report page. |  |  | This feature not developed
|  |  |  | TC_150 | Select the Lead from Lead look up field which is created and save the Visit Report. | 1) Create New Lead from Visit Report 2) Select the Lead which is created from Visit Report 3) Click on Save Button | Visit Report should save with Lead . |  |  | This feature not developed
|  |  |  | TC_151 | Verify Visit Reports object . | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar | User should navigate to "Visit Report" landing page.
|  |  |  | TC_152 | Create Visit Report from Visit Reports object . | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar 3) Click on New button 4) Select Dealer/Lead/NT INST/Technical Service Visit Report 5) Click on Continue button | User should navigate to New Visit Report page.
|  |  |  | TC_153 | Verify all the field sections under New Visit Report page. | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar 3) Click on New button 4) Select Dealer/Lead/NT INST/Technical Service Visit Report 5) Click on Continue button | User should find following field sections along with "Save", "Save New","Cancel" buttons. "Information" , "Branding Related", "Supply chain Related"
|  |  |  | TC_154 | Validate fields under Information Field section. | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar 3) Click on New button 4) Select Dealer/Lead/NT INST/Technical Service Visit Report 5) Click on Continue button | User should find "Visit Report Name" as mandatory text field where user need to enter the name. "Account" as lookup relation field, if user creating visit report for Account user need to select the Account "Lead" as Lookup relation field, if user creating visit report for Lead user need to select the Lead
|  |  |  | TC_155 | Attach image under supply chain related field section | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar 3) Click on New button 4) Select Dealer/Lead/NT INST/Technical Service Visit Report 5) Click on Continue button 6) Click on "link" button under any image to be captured field. 7) Select image from desktop 8) Click on save button. | User should attach required image.
|  |  |  | TC_156 | Create and Save new Visit Report from Visit Reports object . | 1) Login to JSW Application 2) Click on "Visit Reports" Tab on calendar 3) Click on New button 4) Select Dealer/Lead/NT INST/Technical Service Visit Report 5) Click on Continue button 6) Enter all the required fields and click on Save button. | Visit Report should save and visit record also should generate automatically and appear as lookup related field under Visit Report.
|  |  |  | TC_157 | Verify "unplanned visit" Event on Personal Journey plan calendar. | 1) Login to JSW Application 2) Create and save new visit report from visit reports object 3) Navigate to personal journey plan calendar | User should find Unplanned event (Lead/Account..) on calendar.
| Monthly Business Plan |  | Monthly Business Plan: Based on Annual Business plan which is set by Management, Each Sales Officer would create a Monthly Business Plan record by entering the monthly targets for each dealer in trade business associated with him and actuals will be calculated as a roll up of the invoice quantities which are generated to associated Dealer based on month The ASM Monthly Business Plan is built with a roll up the targets and actuals for a month of associated SOs The SSH Monthly Business Plan is built with a roll up the targets and actuals for a month of associated ASMs The ZSH Monthly Business Plan is built with a roll up the targets and actuals for a month of associated SSHs | TC_158 | Login to JSW Application | 1) Enter the URL on selected browser 2) Enter valid User name (SO Credentials) 3) Enter Password 4) Click on Login button | User should able to login application successfully and System should display JSW landing page and it display default "Home" page of Application.
|  |  |  | TC_159 | Select "Monthly Targets" Tab from available Tabs. | 1) Login to JSW Application 2) Select "Monthly Targets" Tab from available Tabs. If "Monthly Targets" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Targets" Tab from list | User should find all existing Monthly Target records if any and "New" button under Monthly Targets page. User can create new Monthly Target by clicking on "New" button.
|  |  |  | TC_160 | Create new "Monthly Target" for SO. | 1) Login to JSW Application with SO Credentials 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. | User should find New Monthly Target landing page.
|  |  |  | TC_161 | Verify all the fields under New "Monthly Target" landing page. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. | User should find following fields along with "Dealer Information" field section. "SO Name" as mandatory and text field. "Product" as pick list field, "Territory" as pick list field, "Year" as text field and "Month" as pick list field, "Get Dealers" and "Save" buttons.
|  |  |  | TC_162 | Validate "SO Name" under Monthly target page. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. | SO Name should auto populate based on login details
|  |  |  | TC_163 | Validate "Year" and "Month" fields under Monthly target page. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. | User should find "Year" field as Text field and user can enter year manually, once enter year user should get month field beside to year field.
|  |  |  | TC_164 | Validate "Month" field under Monthly target page. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Enter Year manually under year field. | User should find "Month" field beside to year field as pick list option and user should select month from picklist.
|  |  |  | TC_165 | Verify all the dealers under Monthly target page. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should find dealers list which are associated under Dealer Information field section.
|  |  |  | TC_166 | Verify all the fields under "Dealer Information" field section. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should find following fields under "Dealer Information" field section. "Dealer Name", "Last Year Same month Actual", "Last Month Actual", "Monthly Target", "Dealer Actual", "Variance".
|  |  |  | TC_167 | Validate "Dealer Name", "Last Year Same month Actual", "Last Month Actual" fields under "Dealer Information" field section. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should find auto populated values with read only mode under "Dealer Name" -- User should find Dealer(Account) name "Last Year Same Month Actual" -- User should find last year same month achievement of Dealer "Last Month Actual" -- User should find Last month achievement of Dealer
|  |  |  | TC_168 | Validate "Monthly Target" field under "Dealer Information" field section. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should enter Dealer monthly target manually under "Monthly Target" text field and this field should accept only numeric numbers.
|  |  |  | TC_169 | Validate "Dealer Actual" field under Dealer Information field section. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should find "Dealer Actual" field with auto populated values as read only field and the value which populates based on the Rollup value of all Invoices generated on selected month for that dealer. (Rollup : Sum up value of all the invoices)
|  |  |  | TC_170 | Validate "Variance" field under Dealer Information field section. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button | User should find "Variance" field with auto populated values , the value should populate based on the formula which is mentioned to calculate the difference (Percentage value%) between last month achievement (Actual) and current month achievement (Actual)
|  |  |  | TC_171 | Save the Monthly target record. | 1) Login to JSW Application with SO Credentials. 2) Select "Monthly Target" Tab from available Tabs. If "Monthly Target" Tab is not available on Application landing page, click on "+" and there we can find "Monthly Target" Tab from list 3) Click on "New" button. 4) Select "Territory","Year","Month" fields 5) Click on "Get Dealers" button 6) Enter Monthly targets under Dealer information field section. 7) Click on Save button. | Record should save and user navigates to monthly targets home page
|  |  |  | TC_172 | Check Sales Officer (SO) monthly target and Monthly Actual fields. | 1) Login to JSW Application with SO Credentials. 2) Create and save Monthly target record. 3) Click on same Monthly target record. | User should navigate to Monthly targets detail page and under "SO Information" field section user should find "SO Monthly Target" and "SO Monthly Actual" fields.
|  |  |  | TC_173 | Validate "Monthly target" field under monthly targets details page. | 1) Login to JSW Application with SO Credentials. 2) Create and save Monthly target record. 3) Click on same Monthly target record. | User should find some value (numeric numbers) automatically under "Monthly target" field, this value should be calculated based on roll ups (Sum up) of the Dealer Monthly Targets which are entered manually.
|  |  |  | TC_174 | Validate "Monthly Actual" field under monthly targets details page. | 1) Login to JSW Application with SO Credentials. 2) Create and save Monthly target record. 3) Click on same Monthly target record. | User should find some value (numeric numbers) automatically under "Monthly actual" field, this value should be calculated based on roll ups (Sum up) of the Dealer Monthly Actuals (Achievements) which are auto populated based on the invoices done for the dealers.
|  |  |  | TC_175 | Verify ASM Monthly Targets. | 1) Login to JSW Application with ASM Credentials. 2) Select "ASM Targets" Tab from available Tabs. If "ASM Targets" Tab is not available on Application landing page, click on "+" and there we can find "ASM Targets" Tab from list | User should navigate to ASM Targets home page.
|  |  |  | TC_176 | Validate "Monthly target" and "Monthly Actual" for ASM | 1) Login to JSW Application with ASM Credentials. 2) Select "ASM Targets" Tab from available Tabs. If "ASM Targets" Tab is not available on Application landing page, click on "+" and there we can find "ASM Targets" Tab from list 3) Click on Available Record under ASM Targets home page. | User should find ASM Target detail page and month wise Targets and Actuals should display automatically. All the Targets and Actuals should calculate at backend based on targets and Actuals of Sos who are reporting should rollups and display .
|  |  |  | TC_177 | Verify SSM Monthly Targets. | 1) Login to JSW Application with SSM Credentials. 2) Select "SSM Targets" Tab from available Tabs. If "SSM Targets" Tab is not available on Application landing page, click on "+" and there we can find "ASM Targets" Tab from list | User should navigate to SSM Targets home page.
|  |  |  | TC_178 | Validate "Monthly target" and "Monthly Actual" for SSM | 1) Login to JSW Application with SSM Credentials. 2) Select "ASM Targets" Tab from available Tabs. If "ASM Targets" Tab is not available on Application landing page, click on "+" and there we can find "SSM Targets" Tab from list 3) Click on Available Record under SSM Targets home page. | User should find SSM Target detail page and month wise Targets and Actuals should display automatically. All the Targets and Actuals should calculate at backend based on targets and Actuals of ASMs who are reporting should rollups and display .
|  |  |  | TC_179 | Verify ZSM Monthly Targets. | 1) Login to JSW Application with ZSM Credentials. 2) Select "ZSM Targets" Tab from available Tabs. If "SSM Targets" Tab is not available on Application landing page, click on "+" and there we can find "ZSM Targets" Tab from list | User should navigate to ZSM Targets home page.
|  |  |  | TC_180 | Validate "Monthly target" and "Monthly Actual" for ZSM | 1) Login to JSW Application with ZSM Credentials. 2) Select "ZSM Targets" Tab from available Tabs. If "ZSM Targets" Tab is not available on Application landing page, click on "+" and there we can find "ZSM Targets" Tab from list 3) Click on Available Record under ZSM Targets home page. | User should find ZSM Target detail page and month wise Targets and Actuals should display automatically. All the Targets and Actuals should calculate at backend based on targets and Actuals of SSMs who are reporting should rollups and display .

## Integration Test Cases
S.No | Module/Sub Module | User Story ID | Use Story Description | Test Case ID | Test Case Description | Test Steps | Expected Result | Actual Result | Status | Comments/Remarks
1 | Customer ( Sold to Party/Stock Transfer) Data integration from Legacy system to SFDC System. | CI_01 | Customer Data Transfer : All the customers (Sold to Party / Depot) should reflect in SFDC system from legacy system based on Schedule run on time basis. | TC_01 | Create/Update Customers in legacy system and Run the Schedules at back end based on the time scheduled. | 1) Run the Schedules at back end automatically based on the time scheduled. | Customer ( Sold to Party/Stock Transfer) Record count should match with legacy system and SFDC , Records should reflect/Update in SFDC application under "Accounts" object.
[5 empty] | Validate field mapping for "Account Group" . | 1) Run the Schedules at back end automatically based on the time scheduled. | Account Group field should update in SFDC and based on this field mapping system segregates and store the data in specific Record type under objects.
[5 empty] | Validate "Sold to party" Account group field. | 1) Run the Schedules at back end automatically based on the time scheduled. | Account Group field for Sold to Party customer should reflect in SFDC and based on this field mapping ,system segregates and store the data under Accounts objects.
[5 empty] | Verify Field mapping for Distribution channel. | 1) Run the Schedules at back end automatically based on the time scheduled. | Based on the bellow distribution channels in legacy system, Records should be created/Updated in Salesforce application. Legacy System -----> SFDC Distribution Channel - 10 -----> "Trade" Record type Distribution Channel- 20 ------> "Non Trade" Record Type
[5 empty] | Validate field mapping for "Ship to party" Account Group . | 1) Run the Schedules at back end automatically based on the time scheduled. | All the Ship to party details should map to relevant customer and based on the selection of Ship to party, following fields should display as per the mappings. "Ship to party code" , "Ship to party name"
[5 empty] | Validated "Depot" Account Group field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | Account Group field for Depot should reflect in SFDC and based on this field mapping system segregates and store the data under Accounts objects as "Depot" Record type.
[5 empty] | Validate all the customer records after schedule run. | 1) Run the Schedules at back end automatically based on the time scheduled. | Customer record count should match and all the customer records should be segregated/Updated based on the Account Group / Distribution channel mapping.
[5 empty] | Validated "Customer Code" field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | Customer code is mandatory field , If customer code finds in both the systems data gets updated accordingly, if customer code is created in legacy system, new Account record gets generated in salesforce.
[5 empty] | Verify Ship to party field mappings. | 1) Run the Schedules at back end automatically based on the time scheduled. | All the Ship to party details should map to customer and based on the selection of Ship to party, following fields should display as per the mappings. "Ship to party code" , "Ship to party name"
[5 empty] | Verify "Address" field mappings. | 1) Run the Schedules at back end automatically based on the time scheduled. | All the following Address fields should map accordingly. "Address" , "Street" , " District", "Pin code", "City","Country","Region","Telephone Number", "Mobile Number"…Etc.
[5 empty] | Validate Credit profile field mappings. | 1) Run the Schedules at back end automatically based on the time scheduled. | Following fields should get update based on schedule run. "Credit Limit", "Credit Available", "Credit Outstanding", "Current Outstanding", "Net Outstanding", "Open Order", "Open Delivery", "Previous credit limit","Valid Up to".
|  | CI_02 | Business Partner Data Transfer : All the Business Partners (Sub Dealers/Sales Promoters/Sales Employee) should reflect in SFDC system from legacy system based on Schedule run on time basis. |  | Run the Schedules at back end based on the time scheduled. | 1) Run the Schedules at back end automatically based on the time scheduled. | Business Partners ( Sub Dealers/Sales Promoters/Sales Employee) Records should reflect/Update in SFDC application under "Business Partners" object.
[5 empty] | Validated "Account Group" field mapping for Business Partner. | 1) Run the Schedules at back end automatically based on the time scheduled. | Based on the bellow Account Group in legacy system, Records should be created/Updated in Salesforce application. Legacy System -----> SFDC Sub Dealer -----> "Sub Dealer" Record type Sales Promoter ------> "Sales Promoter" Record Type Sales Employee -------------> "Sales Employee" Record Type Middle Man Commission ----> "Middle Man Commission" Record type.
[5 empty] | Validate all the Business Partner records after schedule run. | 1) Run the Schedules at back end automatically based on the time scheduled. | Customer record count should match and all the records should be segregated/Updated based on the Account Group mapping.
[5 empty] | Validated "Customer Code" field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | Customer code is mandatory field , If customer code finds in both the systems data gets updated accordingly, if customer code is created in legacy system, new Account record gets generated in salesforce.
[5 empty] | Verify "Address" field mappings. | 1) Run the Schedules at back end automatically based on the time scheduled. | All the following Address fields should map accordingly. "Address" , "Street" , " District", "Pin code", "City","Country","Region","Telephone Number", "Mobile Number"…Etc.
[5 empty] | Verify Field mapping for Distribution channel and Division. | 1) Run the Schedules at back end automatically based on the time scheduled. | All the Distribution Channels and Divisions if any should map to Depot customer under Distribution Channel/Division fields in SFDC system.
|  | SO_03 | Sales Order Data Transfer : All the Sales Orders details should reflect in SFDC system from legacy system based on Schedule run on time basis. |  | Create/Update Orders in legacy system and Run the Schedules at back end based on the time scheduled. | 1) Run the Schedules at back end automatically based on the time scheduled. | Sales Order Record count should match with legacy system and SFDC , Records should reflect/Update in SFDC application under "Order" object.
[5 empty] | Validate SO/STO field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | SO/STO number should appear / update in sfdc as mapped with legacy system.
[5 empty] | Validate Sold to party id and Sold to party Name field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | Sold to party code and sold to party name should appear / update in sfdc as mapped with legacy system.
[5 empty] | Validate Account field mapping. | 1) Run the Schedules at back end automatically based on the time scheduled. | As per the customer code , Account field should update
[5 empty] | Validate below mentioned field mapping. "Plant" , "Order Quantity", "Distribution Channel", "SO/STO Date" | 1) Run the Schedules at back end automatically based on the time scheduled. | Below mentioned fields and all the Sales Order information should update in sfdc as mapped with legacy system. "Plant" , "Order Quantity", "Distribution Channel", "SO/STO Date"
[5 empty] | Verify Order details under Account object. | 1) Create/Update Orders in legacy system and Run the Schedules at back end based on the time scheduled. 2) Navigate to Account's object under SFDC application | All the related Order details should appear under Account object.
|  | Del_04 | SO Delivery Data Transfer : SO Delivery details should reflect in SFDC system from legacy system based on Schedule run on time basis. |  | Validate below mentioned field mapping. "Delivery Quantity" , "Delivery Number", "SO Number", "Sold to code" | 1) Run the Schedules at back end automatically based on the time scheduled. | Below mentioned fields and all the Delivery information should update in sfdc as mapped with legacy system. "Delivery Quantity" , "Delivery Number", "SO Number", "Sold to code"
[5 empty] | Validate below mentioned field mapping for Shipping details. "Ship to party" , "Receiving plant", "Account" | 1) Run the Schedules at back end automatically based on the time scheduled. | Below mentioned fields and all the shipping information for Delivery should update in sfdc as mapped with legacy system. "Ship to party" , "Receiving plant", "Account"
[5 empty] | Validate below mentioned field mapping for Loading details. "Yard Number " , "Yard Entry", "Gross weight measure" | 1) Run the Schedules at back end automatically based on the time scheduled. | Below mentioned fields and all the Loading informtaion for Delivery should update in sfdc as mapped with legacy system. "Yard Number " , "Yard Entry", "Gross weight measure"

## Defects
S.No | Defect description | Defect Raised on | Defect Closed on | QA Status | Remarks
1 | We should restrict user to select duplicate Events (data) on same date | 23/12/2016
2 | Week plan and Day plan is not working accordingly | 23/12/2016 | 26/12/2016 | Working fine
3 | UI Design issues while creating PJP | 26/12/2016 | 26/12/2016 | Still Issue
4 | After editing PJP and save, page is getting saved but it is not redirecting to PJP home page (Not rendering page). | 26/12/2016
5 | “Days Planned” displaying wrong count | 26/12/2016
6 | Planned visit validation is not working. | 26/12/2016
7 | After save a PJP, on hover message of events first letter should start with upper case. | 26/12/2016 | 26/12/2016 | Working fine
8 | After submitting PJP user able to edit the plan | 26/12/2016 | 26/12/2016 | Still Issue
9 | After rejected a PJP, when user send it again for approval getting below Error message | 26/12/2016 | 26/12/2016 | Pending for with QA
10 | Sometimes Hover message is get stuck. | 26/12/2016
11 | After sending PJP for approval , user should not have edit privileges (Edit button shouls not appear) but user able to delete events (Accounts, Leads...) by using single click | 2016-05-01
12 | For Submit week and submit month buttons popup ("Once you submit this record for approval, you might not be able to edit it..." ) is not displaying. | 2016-04-01
13 | If i keep empty in any date under calendar and click on submit week, validation is not working | 2016-04-01
14 | After submitting week plan for approval it is navigating to PJP Edit page | 2016-04-01
15 | If we click on "today" button all the events are disappearing on calendar. | 2016-04-01
16 | When we click on Check in and check out ....Check in time and check out time displaying as error. | 2016-04-01
17 | Eventhough we entered valid address under Lead or Account....address is disappearing while check in and check out the visit record. | 2016-05-01
18 | There should be pop up message (Confirmation Message) while Join the visit. | 2016-05-01
19 | Eventhough we entered valid address under Lead or Account....address is disappearing while check in and check out the visit record. | 2016-06-01
20 | There should be pop up message (Confirmation Message) while Join the visit. | 2016-06-01
21 | Based on the Event (Lead, Account,...) address , Event name is changing automatically | 2016-06-01
22 | Visit Report is not appearing under corresponding Account/Lead/event Pages | 2016-06-01
23 | Under Image capture section in Visit report page, options are not displaying properly. | 2016-11-01
24 | While attaching the image , beside field (stock level jsw) is expanding automatically | 2016-11-01
25 | Need to correct spell check for Influencer under journey plan filer options | 16/1/2016
26 | Cancel option is not working during submitting month plan , Displaying as pending with manager but when login with manager, record is not appearing. | 16/1/2016
27 | Edit option need to remove under Journey plan after send for approval. | 16/1/2016
28 | Year format (Displaying as currency) should change under Monthly target for SO | 16/1/2016